## WBS
WBS Code | Task / Subtask | Description | Assigned Dev | Duration (days) | Predecessor(s) | Start Date (Planned) | Deadline (Planned) | Date Started (Actual) | Date Finished (Actual) | Status
0.0 | Project Planning & Design | Review the source baseline and close scope/design decisions before affected implementation begins. |  | 8 | - | 2026-10-12 | 2026-10-19 |  |  | Not Started
0.1 | Requirements & Scope Review | Establish the reviewed requirements and project boundaries. |  | 4 | - | 2026-10-12 | 2026-10-15 |  |  | Not Started
0.1.1 | Review Source Artifacts | Study SRS, development agreement, ERD, UI PDF, HLD, LLD and web architecture. | Dev 1 (UI) | 2 | - | 2026-10-12 | 2026-10-13 |  |  | Not Started
0.1.2 | Confirm Roles, School Domain & Permissions | Confirm Student/Organizer/Admin roles, account activation, domain allowlist and permission matrix. (OD-001, OD-002) | Client + Dev | 2 | 0.1.1 | 2026-10-14 | 2026-10-15 |  |  | Not Started
0.1.3 | Build Requirements Traceability | Map functional requirements, 13 screen groups and AT-001 to AT-010 to work packages. | Dev 1 (UI) | 2 | 0.1.1 | 2026-10-14 | 2026-10-15 |  |  | Not Started
0.2 | Architecture, Data & Policy Decisions | Record approvals for proposals/TBDs instead of treating them as approved requirements. |  | 3 | - | 2026-10-16 | 2026-10-18 |  |  | Not Started
0.2.1 | Confirm React/Vite, Blade & API Boundary | Confirm React as primary UI, Blade use, API prefix/versioning and auth/session/CSRF/CORS approach. (HLD D-03; OD-016) | Client + Dev | 2 | 0.1.2 | 2026-10-16 | 2026-10-17 |  |  | Not Started
0.2.2 | Approve Schema Gaps & State Rules | Decide status enums/transitions, registration uniqueness/waitlist, profile fields, categories, moderation and supporting tables. (OD-004 to OD-006, OD-011) | Client + Dev | 2 | 0.1.2, 0.1.3 | 2026-10-16 | 2026-10-17 |  |  | Not Started
0.2.3 | Approve QR, Notifications, CSV & Privacy Rules | Close QR expiry/replay, manual overrides, provider/retries, export fields, retention/timezone and performance/accessibility targets. (OD-007 to OD-015) | Client + Dev | 3 | 0.1.2 | 2026-10-16 | 2026-10-18 |  |  | Not Started
0.3 | UI & Test Baseline | Map the screen baseline into development and testing work. |  | 4 | - | 2026-10-16 | 2026-10-19 |  |  | Not Started
0.3.1 | Map 13 Screens to Routes and Roles | Map login, account, student, organizer, admin, attendance and logout screens to role-aware navigation. | Dev 1 (UI) | 2 | 0.1.3, 0.1.2 | 2026-10-16 | 2026-10-17 |  |  | Not Started
0.3.2 | Define Shared UI Components & States | Define responsive layouts, forms, loading/error/empty/success states and QR/manual fallback controls. | Dev 1 (UI) | 2 | 0.3.1 | 2026-10-18 | 2026-10-19 |  |  | Not Started
0.3.3 | Outline Test Plan & Acceptance Evidence | Prepare test cases for roles, capacity, attendance states, QR security, reports and deployment. | SQA | 1 | 0.1.3 | 2026-10-16 | 2026-10-16 |  |  | Not Started
1.0 | Platform Foundation & Shared Architecture | Set up the approved React/Vite + Laravel/PHP + MySQL development baseline. |  | 7 | - | 2026-10-18 | 2026-10-24 |  |  | Not Started
1.1 | Frontend Setup | Create the shared React frontend shell. |  | 4 | - | 2026-10-18 | 2026-10-21 |  |  | Not Started
1.1.1 | Initialize React/Vite Application | Set up HTML, CSS, JavaScript, React and Vite project structure. | Dev 1 (UI) | 1 | 0.2.1 | 2026-10-18 | 2026-10-18 |  |  | Not Started
1.1.2 | Configure Router, Layouts & Reusable Controls | Add public/student/organizer/admin shells, navigation and common UI controls. | Dev 1 (UI) | 2 | 1.1.1, 0.3.2 | 2026-10-20 | 2026-10-21 |  |  | Not Started
1.2 | Laravel Backend Setup | Create server-side routing, validation and response contracts. |  | 3 | - | 2026-10-18 | 2026-10-20 |  |  | Not Started
1.2.1 | Initialize Laravel 13 / PHP Application | Configure the Laravel project and base application structure. | Dev 2 (API) | 1 | 0.2.1 | 2026-10-18 | 2026-10-18 |  |  | Not Started
1.2.2 | Configure API Routes & JSON Error Contract | Set approved route versioning, response envelope, pagination and validation-error handling. | Dev 2 (API) | 1 | 1.2.1, 0.2.1 | 2026-10-19 | 2026-10-19 |  |  | Not Started
1.2.3 | Configure Authentication & Request Security | Implement approved session/auth approach, CSRF/CORS settings and role middleware defaults. | Dev 2 (API) | 2 | 1.2.1, 0.2.1 | 2026-10-19 | 2026-10-20 |  |  | Not Started
1.3 | Database & Persistence Foundation | Implement the five ERD baseline entities and approved support schema. |  | 7 | - | 2026-10-18 | 2026-10-24 |  |  | Not Started
1.3.1 | Translate Five ERD Entities to Migration Plan | Document keys and relationships for users, event_organizers, events, registrations and attendances. | Dev 3 (DB) | 1 | 0.2.2 | 2026-10-18 | 2026-10-18 |  |  | Not Started
1.3.2 | Create Core Migrations, Models & Relationships | Build the relational system of record with approved keys, foreign keys and constraints. |  | 4 | - | 2026-10-19 | 2026-10-22 |  |  | Not Started
1.3.2.1 | Create Users & Organizer Migrations | Implement users and event_organizers fields/relations from the supplied ERD. | Dev 3 (DB) | 1 | 1.3.1 | 2026-10-19 | 2026-10-19 |  |  | Not Started
1.3.2.2 | Create Event, Registration & Attendance Migrations | Implement events, registrations and attendances with the ERD relationships. | Dev 3 (DB) | 2 | 1.3.2.1 | 2026-10-20 | 2026-10-21 |  |  | Not Started
1.3.2.3 | Add Relations, Integrity Constraints & Indexes | Add approved foreign keys, uniqueness/index rules and Eloquent relationships. | Dev 3 (DB) | 1 | 1.3.2.2 | 2026-10-22 | 2026-10-22 |  |  | Not Started
1.3.3 | Add Approved Supporting Schema | Add profile/photo, event QR, preferences, moderation and audit persistence only after approval; these are gaps in the five-table ERD. | Dev 3 (DB) | 2 | 1.3.2.3, 0.2.2, 0.2.3 | 2026-10-23 | 2026-10-24 |  |  | Not Started
1.4 | Development Quality & Environment | Prepare local configuration and repeatable checks. |  | 1 | - | 2026-10-19 | 2026-10-19 |  |  | Not Started
1.4.1 | Configure Local Environment, Secrets & Logs | Document environment variables, protect credentials and configure useful application logging. | Dev 4 (Ops) | 1 | 1.2.1 | 2026-10-19 | 2026-10-19 |  |  | Not Started
1.4.2 | Configure Test Tooling & Basic CI Checks | Set up unit/feature-test execution and basic build/lint checks for frontend and backend. | Dev 4 (Ops) | 1 | 1.1.1, 1.2.1 | 2026-10-19 | 2026-10-19 |  |  | Not Started
2.0 | Identity & Account Management | Support registration, login/logout, role-aware access and profile/security screens. |  | 7 | - | 2026-10-21 | 2026-10-27 |  |  | Not Started
2.1 | Login, Logout & Role Access | Authentication and session protection. (FR-AUTH-001, FR-AUTH-002, FR-AUTH-006) |  | 5 | - | 2026-10-22 | 2026-10-26 |  |  | Not Started
2.1.1 | Build Login & Logout Confirmation Screens | Create role selector, school email/password, remember-me and logout confirmation UI. (Screens 01, 13) | Dev 1 (UI) | 1 | 1.1.2 | 2026-10-22 | 2026-10-22 |  |  | Not Started
2.1.2 | Implement Login/Logout Session Flow | Authenticate using server-side role data and invalidate the session at logout. | Dev 2 (API) | 2 | 1.2.3, 1.3.2.3 | 2026-10-23 | 2026-10-24 |  |  | Not Started
2.1.3 | Enforce Role-Aware Routes & Policies | Restrict Student, Organizer and Admin routes/actions on the server; do not trust client role values. | Dev 2 (API) | 2 | 2.1.2 | 2026-10-25 | 2026-10-26 |  |  | Not Started
2.2 | Create Account & School Verification | Build official school email account creation with required fields. (FR-AUTH-003 to FR-AUTH-005) |  | 3 | - | 2026-10-21 | 2026-10-23 |  |  | Not Started
2.2.1 | Build Account Creation Flow | Capture name, school Gmail, password/confirmation, role and Terms/Privacy acceptance. (Screen 02) | Dev 1 (UI) | 2 | 1.1.2, 0.3.1 | 2026-10-22 | 2026-10-23 |  |  | Not Started
2.2.2 | Implement School-Domain Verification | Validate the configured domain allowlist and implement the approved email verification flow. | Dev 2 (API) | 2 | 0.2.2, 1.2.3 | 2026-10-21 | 2026-10-22 |  |  | Not Started
2.2.3 | Validate Registration & Hash Passwords | Validate required data server-side and never store passwords in plaintext. | Dev 2 (API) | 1 | 2.2.2, 1.3.2.3 | 2026-10-23 | 2026-10-23 |  |  | Not Started
2.3 | My Account, Profile & Preferences | Provide profile details, photo, password and notification preferences. (FR-AUTH-007, FR-STU-006, FR-NOT-001) |  | 5 | - | 2026-10-22 | 2026-10-26 |  |  | Not Started
2.3.1 | Build Profile & Account Form | Create profile display/edit screen for personal information and security settings. (Screen 07) | Dev 1 (UI) | 1 | 1.1.2, 0.3.2 | 2026-10-22 | 2026-10-22 |  |  | Not Started
2.3.2 | Persist Approved Profile Fields & Photo | Implement profile/course/student-ID fields and image storage only per approved schema and privacy rules. | Dev 3 (DB) | 2 | 1.3.3, 2.3.1 | 2026-10-25 | 2026-10-26 |  |  | Not Started
2.3.3 | Implement Password Change & Notification Preferences | Persist permitted password updates and reminder/attendance-confirmation preference settings. | Dev 2 (API) | 2 | 2.1.2, 1.3.3 | 2026-10-25 | 2026-10-26 |  |  | Not Started
2.4 | Password Recovery (Conditional) | The SRS shows Forgot password but marks the detailed workflow/provider as TBD. |  | 4 | - | 2026-10-24 | 2026-10-27 |  |  | Not Started
2.4.1 | Confirm Recovery Scope and Provider | Confirm recovery identity checks, email provider and token expiry; implement only if included in approved scope. (OD-003) | Client + Dev | 2 | 0.2.3, 2.2.3 | 2026-10-24 | 2026-10-25 |  |  | Not Started
2.4.2 | Implement Approved Recovery Flow if Required | Conditional work package; keep out of release scope until the recovery design is approved. | Dev 2 (API) | 2 | 2.4.1 | 2026-10-26 | 2026-10-27 |  |  | Not Started
3.0 | Student Event Discovery & Registration | Students discover events, view their registrations and register within capacity rules. |  | 19 | - | 2026-10-22 | 2026-11-09 |  |  | Not Started
3.1 | Student Dashboard | Student self-service summary. (FR-STU-001, FR-STU-002) |  | 14 | - | 2026-10-27 | 2026-11-09 |  |  | Not Started
3.1.1 | Show Summary Metrics & Upcoming Registered Events | Build student dashboard cards and upcoming registered-event list. (Screen 03) | Dev 1 (UI) | 1 | 2.1.3, 1.3.2.3 | 2026-10-27 | 2026-10-27 |  |  | Not Started
3.1.2 | Connect Recent Attendance & Quick Actions | Show recent attendance and direct Attendance In/Out actions using persisted attendance data. | Dev 1 (UI) | 1 | 3.1.1, 5.2.3, 5.3.3 | 2026-11-09 | 2026-11-09 |  |  | Not Started
3.2 | Browse Events | Search, filter, sort and view published event details. (FR-STU-003, FR-STU-004) |  | 13 | - | 2026-10-22 | 2026-11-03 |  |  | Not Started
3.2.1 | Build Event List, Search, Filters & Detail UI | Implement search by name/organizer/topic, category filters, sort, venue/date/time and capacity display. (Screen 06) | Dev 1 (UI) | 2 | 1.1.2, 0.3.2 | 2026-10-22 | 2026-10-23 |  |  | Not Started
3.2.2 | Implement Published Event Catalogue API | Return authorized published event list/details and capacity based on server-side rules. | Dev 2 (API) | 2 | 1.2.2, 1.3.2.3, 4.2.2 | 2026-11-01 | 2026-11-02 |  |  | Not Started
3.2.3 | Connect Event Details & Registration Action | Wire browse/details UI to event API and registration service with clear success/error feedback. | Dev 1 (UI) | 1 | 3.2.1, 3.2.2, 3.3.2 | 2026-11-03 | 2026-11-03 |  |  | Not Started
3.3 | Registration Service & My Registrations | Persist user-event registrations, enforce capacity, and show status. (FR-REG-001 to FR-REG-005) |  | 14 | - | 2026-10-23 | 2026-11-05 |  |  | Not Started
3.3.1 | Implement Transactional Registration & Capacity | Registration decisions must be server-side and race-safe. |  | 4 | - | 2026-10-23 | 2026-10-26 |  |  | Not Started
3.3.1.1 | Implement Registration Service & Capacity Check | Validate event availability and reserve capacity within a database transaction. | Dev 2 (API) | 2 | 1.2.2, 1.3.2.3, 0.2.2 | 2026-10-23 | 2026-10-24 |  |  | Not Started
3.3.1.2 | Apply Uniqueness, Waitlist & Cancellation Rules | Implement only approved user/event uniqueness, waiting-list and cancellation behavior. | Dev 3 (DB) | 2 | 3.3.1.1, 0.2.2 | 2026-10-25 | 2026-10-26 |  |  | Not Started
3.3.2 | Build My Registrations & Status List | Show the current student's registration records and approved status values. (Screen/navigation) | Dev 1 (UI) | 1 | 1.1.2, 3.3.1.2 | 2026-10-27 | 2026-10-27 |  |  | Not Started
3.3.3 | Connect Registration Confirmation Outcome | Show persisted result and enqueue confirmation only when provider, event setting and user preference enable it. | Dev 2 (API) | 1 | 3.3.1.2, 8.2.1 | 2026-11-05 | 2026-11-05 |  |  | Not Started
4.0 | Organizer Event Management & QR Setup | Organizers create events, manage lifecycle, and issue separate arrival/departure QR codes. |  | 13 | - | 2026-10-22 | 2026-11-03 |  |  | Not Started
4.1 | Create & Edit Event | Build and persist event details. (FR-EVT-001, FR-EVT-006) |  | 7 | - | 2026-10-22 | 2026-10-28 |  |  | Not Started
4.1.1 | Build Event Create/Edit Form | Capture title, category, capacity, date, start/end time, venue and description. (Screen 09) | Dev 1 (UI) | 2 | 1.1.2, 0.3.1 | 2026-10-22 | 2026-10-23 |  |  | Not Started
4.1.2 | Validate and Persist Event & Organizer Ownership | Apply server-side validation and retain creator/organizer references consistent with the ERD. | Dev 2 (API) | 2 | 1.2.2, 1.3.2.3, 2.1.3 | 2026-10-27 | 2026-10-28 |  |  | Not Started
4.2 | Draft, Publish & Registration Settings | Keep event visibility and allowed state transitions server-controlled. (FR-EVT-002, FR-EVT-003, FR-EVT-007) |  | 3 | - | 2026-10-29 | 2026-10-31 |  |  | Not Started
4.2.1 | Implement Draft/Publish Transition Rules | Save drafts and publish only through approved states and authorized ownership. | Dev 2 (API) | 2 | 4.1.2, 0.2.2 | 2026-10-29 | 2026-10-30 |  |  | Not Started
4.2.2 | Expose Published Events & Registration Settings | Apply public listing rules and approved settings for school email and confirmations. | Dev 2 (API) | 1 | 4.2.1 | 2026-10-31 | 2026-10-31 |  |  | Not Started
4.3 | Event QR Code Management | Issue separate Attendance In and Attendance Out QR codes. (FR-EVT-004, FR-EVT-005) |  | 10 | - | 2026-10-25 | 2026-11-03 |  |  | Not Started
4.3.1 | Finalize Event QR Persistence & Token Protocol | Use approved opaque token design, action/event binding, expiry, refresh and revocation rules. | Dev 3 (DB) | 2 | 0.2.3, 1.3.3 | 2026-10-25 | 2026-10-26 |  |  | Not Started
4.3.2 | Generate Separate IN/OUT QR Codes | Generate action-specific event QR codes and make them available to authorized organizers. |  | 2 | - | 2026-10-31 | 2026-11-01 |  |  | Not Started
4.3.2.1 | Generate Action-Specific QR Tokens | Issue distinct IN and OUT token material tied to the selected event. | Dev 2 (API) | 1 | 4.3.1, 4.2.1 | 2026-10-31 | 2026-10-31 |  |  | Not Started
4.3.2.2 | Render & Download QR Codes | Display and download the separate codes in the event setup interface. (Screen 09) | Dev 1 (UI) | 1 | 4.3.2.1 | 2026-11-01 | 2026-11-01 |  |  | Not Started
4.3.3 | Refresh, Revoke & Expire QR Codes | Refresh one action code without leaving the prior token usable; handle stale/invalid token feedback. | Dev 2 (API) | 2 | 4.3.2.2 | 2026-11-02 | 2026-11-03 |  |  | Not Started
5.0 | QR & Manual Attendance In/Out | Record attendance linked to a student's event registration using QR or approved manual fallback. |  | 14 | - | 2026-10-28 | 2026-11-10 |  |  | Not Started
5.1 | QR Scanner & Manual Fallback UI | Provide the camera interface and manual path. (Screens 04, 05) |  | 2 | - | 2026-10-28 | 2026-10-29 |  |  | Not Started
5.1.1 | Build Browser Camera / QR Scanner Interface | Implement camera permission handling, scanner feedback and decoder adapter. | Dev 1 (UI) | 2 | 1.1.2 | 2026-10-28 | 2026-10-29 |  |  | Not Started
5.1.2 | Build Manual Attendance Fallback Forms | Collect approved student identity/event inputs when QR scanning is unavailable. | Dev 1 (UI) | 1 | 1.1.2 | 2026-10-28 | 2026-10-28 |  |  | Not Started
5.2 | Attendance In | Check in only a registered, authorized user and persist server time. (FR-ATT-001, FR-ATT-002, FR-ATT-005) |  | 5 | - | 2026-11-01 | 2026-11-05 |  |  | Not Started
5.2.1 | Validate QR Action, Event & Registration | Validate token action/expiry and prove the authenticated user has the matching registration. | Dev 2 (API) | 2 | 4.3.2.1, 3.3.1.2, 1.3.2.3 | 2026-11-01 | 2026-11-02 |  |  | Not Started
5.2.2 | Persist time_in and Active Status | Create/update attendance transactionally using server-generated time_in, not browser timestamps. | Dev 2 (API) | 2 | 5.2.1 | 2026-11-03 | 2026-11-04 |  |  | Not Started
5.2.3 | Connect Attendance In UI & Confirmation | Wire QR/manual paths to API; validate school Gmail/profile match and show clear result states. | Dev 1 (UI) | 1 | 5.1.1, 5.1.2, 5.2.2 | 2026-11-05 | 2026-11-05 |  |  | Not Started
5.3 | Attendance Out | Close an active attendance session and persist server time_out. (FR-ATT-003, FR-ATT-004) |  | 4 | - | 2026-11-05 | 2026-11-08 |  |  | Not Started
5.3.1 | Show Active Session & Checkout Confirmation | Display event, check-in time and duration before checkout. (Screen 05) | Dev 1 (UI) | 1 | 5.2.2, 1.1.2 | 2026-11-05 | 2026-11-05 |  |  | Not Started
5.3.2 | Validate Active Session & Persist time_out | Require an active session; set server time_out and completed status transactionally. | Dev 2 (API) | 2 | 5.3.1, 4.3.2.1 | 2026-11-06 | 2026-11-07 |  |  | Not Started
5.3.3 | Connect QR/Manual Checkout & Feedback | Wire checkout actions, confirmation and closed-session response to the attendance API. | Dev 1 (UI) | 1 | 5.1.1, 5.1.2, 5.3.2 | 2026-11-08 | 2026-11-08 |  |  | Not Started
5.4 | Attendance Integrity & Duplicate Handling | Protect against stale tokens and conflicting/repeated scans. (FR-ATT-006: exact behavior TBD) |  | 3 | - | 2026-11-08 | 2026-11-10 |  |  | Not Started
5.4.1 | Enforce Duplicate, Replay & Concurrency Safeguards | Apply approved duplicate-scan, re-entry and idempotency behavior with transaction guards. | Dev 3 (DB) | 2 | 5.2.2, 5.3.2, 0.2.3 | 2026-11-08 | 2026-11-09 |  |  | Not Started
5.4.2 | Test Attendance State Transitions | Test valid, expired, wrong-action, already-active and inactive-session check-in/out attempts. | SQA | 1 | 5.4.1 | 2026-11-10 | 2026-11-10 |  |  | Not Started
6.0 | Organizer Operations & Reporting | Provide dashboards, attendee operations, registration pipeline and CSV export. |  | 14 | - | 2026-10-29 | 2026-11-11 |  |  | Not Started
6.1 | Organizer Dashboard | Summaries for organizer-owned events. (FR-ORG-001, FR-ORG-002) |  | 3 | - | 2026-11-08 | 2026-11-10 |  |  | Not Started
6.1.1 | Calculate Event, Registration & Attendance Metrics | Query event counts, registrations, check-ins/no-shows and approved show-up-rate definition. | Dev 3 (DB) | 2 | 4.2.2, 3.3.1.2, 5.2.2, 5.3.2 | 2026-11-08 | 2026-11-09 |  |  | Not Started
6.1.2 | Build Upcoming/Recent Events Dashboard UI | Display organizer's upcoming events and recent event performance. (Screen 08) | Dev 1 (UI) | 1 | 6.1.1 | 2026-11-10 | 2026-11-10 |  |  | Not Started
6.2 | Attendees by Event | Show only attendee data for an authorized organizer/event. (FR-ATT-O-001 to FR-ATT-O-005) |  | 4 | - | 2026-11-08 | 2026-11-11 |  |  | Not Started
6.2.1 | Implement Scoped Attendee Query & Counts | Return status counts and registration/check-in/check-out details only for authorized event scope. | Dev 3 (DB) | 2 | 1.3.2.3, 5.2.2, 5.3.2 | 2026-11-08 | 2026-11-09 |  |  | Not Started
6.2.2 | Build Attendee Search, Filters & Table | Search/filter/paginate attendee list and show approved personal and attendance fields. (Screen 10) | Dev 1 (UI) | 2 | 6.2.1, 4.2.2 | 2026-11-10 | 2026-11-11 |  |  | Not Started
6.3 | Upcoming Registration Pipeline | Organizer registration operations. (FR-REG-002, FR-REG-005, FR-ORG-003, FR-ORG-004) |  | 4 | - | 2026-10-29 | 2026-11-01 |  |  | Not Started
6.3.1 | Implement Scoped Registration Search & Statuses | Search by name/ID/email/course and show approved registration/waitlist statuses; confirm profile-field schema. | Dev 3 (DB) | 2 | 3.3.1.2, 1.3.3, 0.2.2 | 2026-10-29 | 2026-10-30 |  |  | Not Started
6.3.2 | Build Registration Pipeline & Reminder Action | Add event filters, status visibility, export/reminder actions; reminder channel/provider remains approval-gated. | Dev 1 (UI) | 2 | 6.3.1, 0.2.3 | 2026-10-31 | 2026-11-01 |  |  | Not Started
6.4 | CSV Export | Export only approved fields within the caller's authorization scope. |  | 14 | - | 2026-10-29 | 2026-11-11 |  |  | Not Started
6.4.1 | Approve CSV Fields, Scope & Encoding | Agree columns, timezone/encoding and formula handling before final export implementation. (OD-010) | Client + Dev | 2 | 0.2.3 | 2026-10-29 | 2026-10-30 |  |  | Not Started
6.4.2 | Generate Safe CSV Export | Build the authorized event-attendee/registration CSV export. |  | 2 | - | 2026-11-10 | 2026-11-11 |  |  | Not Started
6.4.2.1 | Query Approved Columns Within Event Scope | Retrieve filtered rows with resource-level authorization and approved columns. | Dev 3 (DB) | 1 | 6.2.1, 6.4.1 | 2026-11-10 | 2026-11-10 |  |  | Not Started
6.4.2.2 | Sanitize Output and Stream CSV Download | Handle formula-leading text and return a downloadable CSV. (AT-009) | Dev 3 (DB) | 1 | 6.4.2.1 | 2026-11-11 | 2026-11-11 |  |  | Not Started
6.5 | Organizer Profile | Manage the organization profile linked to the organizer account. |  | 1 | - | 2026-10-29 | 2026-10-29 |  |  | Not Started
6.5.1 | Build Organization Name & Contact Profile | View/update event_organizers organization_name and contact_number within ownership rules. | Dev 2 (API) | 1 | 1.3.2.3, 2.1.3 | 2026-10-29 | 2026-10-29 |  |  | Not Started
7.0 | Admin Controls, Moderation & Audit | Platform-level controls require the approved admin permission matrix. |  | 11 | - | 2026-11-03 | 2026-11-13 |  |  | Not Started
7.1 | Admin Dashboard & User Management | Build the platform navigation and account controls. (FR-ADM-001, FR-ADM-002) |  | 3 | - | 2026-11-03 | 2026-11-05 |  |  | Not Started
7.1.1 | Build Admin Dashboard Shell & Navigation | Provide Overview, Users, Organizers, Events, Settings, Reports, Attendance and Audit Log navigation. (Screen 12) | Dev 1 (UI) | 1 | 1.1.2, 2.1.3 | 2026-11-03 | 2026-11-03 |  |  | Not Started
7.1.2 | Implement User Listing & Role Administration | Search/view users and perform only approved role/account management actions. | Dev 2 (API) | 2 | 7.1.1, 2.1.3 | 2026-11-04 | 2026-11-05 |  |  | Not Started
7.2 | Organizer & Event Review | Support organizer application and event submission moderation. (FR-ADM-003, FR-ADM-004) |  | 4 | - | 2026-11-04 | 2026-11-07 |  |  | Not Started
7.2.1 | Implement Organizer/Event Review Workflow | Persist review states and authorized decisions; requires approval of supporting schema and permission matrix. | Dev 2 (API) | 2 | 0.2.2, 1.3.3, 7.1.1 | 2026-11-04 | 2026-11-05 |  |  | Not Started
7.2.2 | Implement Flagged Item Review & Outcomes | Expose configured flags/credential issues and record moderation outcome with required audit action. | Dev 2 (API) | 2 | 7.2.1, 7.4.1 | 2026-11-06 | 2026-11-07 |  |  | Not Started
7.3 | Admin Attendance, Settings & Reports | Provide authorized platform-level information and operations. |  | 2 | - | 2026-11-12 | 2026-11-13 |  |  | Not Started
7.3.1 | Build Admin Attendance and Report Views | Provide approved platform reports, attendance oversight and settings screens. | Dev 3 (DB) | 2 | 7.1.1, 6.2.1, 6.4.2.2 | 2026-11-12 | 2026-11-13 |  |  | Not Started
7.4 | Audit Log | Persist and display accountable platform actions. (FR-ADM-005, FR-ADM-006) |  | 7 | - | 2026-11-03 | 2026-11-09 |  |  | Not Started
7.4.1 | Approve Audit Schema & Retention Rules | Confirm audit fields, retention, immutability and export policy before persistence design. | Client + Dev | 2 | 0.2.2, 0.2.3 | 2026-11-03 | 2026-11-04 |  |  | Not Started
7.4.2 | Persist Audited Actions & Build Audit Log View | Record required actor/time/outcome and show audit events to authorized admins. (AT-010) | Dev 3 (DB) | 2 | 7.4.1, 7.1.1, 7.2.2 | 2026-11-08 | 2026-11-09 |  |  | Not Started
8.0 | Notifications & Background Jobs | Configure Redis-backed queues, queue worker and scheduler for approved asynchronous work. |  | 6 | - | 2026-11-03 | 2026-11-08 |  |  | Not Started
8.1 | Queue & Provider Infrastructure | Background execution and provider credentials. |  | 1 | - | 2026-11-03 | 2026-11-03 |  |  | Not Started
8.1.1 | Configure Redis Queue, Worker & Scheduler | Configure development/staging queue transport, worker processing and scheduled-task entry point. | Dev 4 (Ops) | 1 | 1.4.1, 0.2.3 | 2026-11-03 | 2026-11-03 |  |  | Not Started
8.1.2 | Configure Approved Email Provider & Templates | Set provider credentials, sender/template settings and failure policy after Client selection. | Dev 4 (Ops) | 1 | 1.4.1, 0.2.3 | 2026-11-03 | 2026-11-03 |  |  | Not Started
8.2 | Registration & Attendance Notifications | Send only notifications enabled by approved event/user settings. |  | 5 | - | 2026-11-04 | 2026-11-08 |  |  | Not Started
8.2.1 | Implement Registration Confirmation Job | Queue confirmation after transaction commit; ensure retry behavior avoids duplicate side effects. | Dev 2 (API) | 1 | 8.1.1, 8.1.2, 3.3.1.2 | 2026-11-04 | 2026-11-04 |  |  | Not Started
8.2.2 | Implement Attendance Receipt Job | Send approved check-in/out receipt using persisted attendance values and server timestamps. | Dev 2 (API) | 1 | 8.1.1, 8.1.2, 5.2.2, 5.3.2 | 2026-11-08 | 2026-11-08 |  |  | Not Started
8.3 | Scheduled Reminders & Reliability | Recurring reminders and safe retry handling. |  | 2 | - | 2026-11-04 | 2026-11-05 |  |  | Not Started
8.3.1 | Implement Reminder Scheduler & Retry Controls | Select eligible registrations in the approved reminder window, deduplicate sends and record delivery outcome. | Dev 4 (Ops) | 2 | 8.1.1, 8.1.2, 6.3.2 | 2026-11-04 | 2026-11-05 |  |  | Not Started
9.0 | Security, Testing & Quality Assurance | Verify functional acceptance, authorization, privacy, concurrency and release readiness. |  | 15 | - | 2026-11-15 | 2026-11-29 |  |  | Not Started
9.1 | Security & Privacy Hardening | Apply server-side authorization and minimize exposure of personal data. |  | 2 | - | 2026-11-15 | 2026-11-16 |  |  | Not Started
9.1.1 | Review Role/Ownership Authorization & Data Exposure | Test denied cross-organizer access, role bypass, account/session behavior and personal-detail exposure. | SQA | 1 | 2.1.3, 7.1.2, 6.2.2, 7.2.2 | 2026-11-15 | 2026-11-15 |  |  | Not Started
9.1.2 | Review Input Validation, API Errors & Sensitive Logs | Verify request validation, safe error payloads and suppression of secrets/raw QR tokens in logs. | Dev 2 (API) | 1 | 1.2.2, 8.2.2 | 2026-11-15 | 2026-11-15 |  |  | Not Started
9.1.3 | Review Privacy, Responsive UI & Accessibility Baseline | Check approved personal-data visibility/retention rules and agreed browser/accessibility target; exact target must be confirmed. | SQA | 2 | 0.2.3, 2.3.2, 6.2.2, 7.3.1 | 2026-11-15 | 2026-11-16 |  |  | Not Started
9.1.4 | Test QR Expiry, Wrong-Action & Replay Controls | Verify expired/wrong event/wrong action/stale token behavior and no unauthorized attendance transition. | SQA | 1 | 4.3.3, 5.4.1 | 2026-11-15 | 2026-11-15 |  |  | Not Started
9.2 | Cross-Module Integration Freeze | Build an integrated candidate before final acceptance testing. |  | 1 | - | 2026-11-17 | 2026-11-17 |  |  | Not Started
9.2.1 | Run Integration Checklist & Freeze Release Candidate | Verify auth, registration/capacity, event publishing, QR/manual attendance, reports, admin/audit and notifications work together. | Dev 4 (Ops) | 1 | 3.1.2, 3.2.3, 3.3.3, 4.3.3, 5.4.2, 6.4.2.2, 6.5.1, 7.4.2, 8.3.1, 9.1.1, 9.1.2, 9.1.3, 9.1.4 | 2026-11-17 | 2026-11-17 |  |  | Not Started
9.3 | Testing & Acceptance | Run the test levels listed in the LLD and execute SRS acceptance scenarios. |  | 12 | - | 2026-11-18 | 2026-11-29 |  |  | Not Started
9.3.1 | Run Unit and Service Tests | Cover capacity decisions, event transitions, QR outcomes, registration state and CSV sanitation. | SQA | 2 | 9.2.1 | 2026-11-18 | 2026-11-19 |  |  | Not Started
9.3.2 | Run Frontend Component & Browser Tests | Test role navigation, field errors, loading states, camera fallback and success/failure messages. | SQA | 2 | 9.2.1 | 2026-11-18 | 2026-11-19 |  |  | Not Started
9.3.3 | Run API & Integration Tests | Test Laravel authorization, MySQL transactions, Redis jobs, token validation and retry/idempotency. | SQA | 3 | 9.3.1, 9.3.2 | 2026-11-20 | 2026-11-22 |  |  | Not Started
9.3.4 | Execute AT-001 to AT-010 | Acceptance suite traceable to the SRS scenarios. |  | 3 | - | 2026-11-23 | 2026-11-25 |  |  | Not Started
9.3.4.1 | Test Account, Registration & Event Workflows | Run AT-001, AT-002, AT-003 and AT-007; capture expected outcomes and defects. | SQA | 1 | 9.3.3 | 2026-11-23 | 2026-11-23 |  |  | Not Started
9.3.4.2 | Test Attendance & QR Workflows | Run AT-004, AT-005, AT-006 and AT-008; verify timestamps, active sessions and QR rules. | SQA | 1 | 9.3.4.1 | 2026-11-24 | 2026-11-24 |  |  | Not Started
9.3.4.3 | Test CSV Export & Admin Review | Run AT-009 and AT-010; verify scoped export and moderation/audit outcomes. | SQA | 1 | 9.3.4.2 | 2026-11-25 | 2026-11-25 |  |  | Not Started
9.3.5 | Run Security & Concurrency Regression Tests | Test role/ownership bypass, capacity race for final seat, repeated scans and concurrent attendance. | SQA | 2 | 9.3.3, 9.3.4.3 | 2026-11-26 | 2026-11-27 |  |  | Not Started
9.3.6 | Conduct UAT, Fix Defects & Obtain Sign-Off | Walk through approved requirements with stakeholders and correct verified in-scope defects. (Contract §10) | QA 1 / Client | 2 | 9.3.5 | 2026-11-28 | 2026-11-29 |  |  | Not Started
10.0 | Deployment, Handover & Release | Deploy the approved browser application to the supplied Linux/Nginx/PHP-FPM architecture. |  | 7 | - | 2026-11-30 | 2026-12-06 |  |  | Not Started
10.1 | Production Server Setup | Prepare production services and HTTPS. |  | 3 | - | 2026-11-30 | 2026-12-02 |  |  | Not Started
10.1.1 | Provision Linux VPS & Application Services | Configure Nginx, PHP-FPM, Laravel 13, MySQL 8.4 LTS and Redis on the approved server. | Dev 4 (Ops) | 2 | 9.3.6 | 2026-11-30 | 2026-12-01 |  |  | Not Started
10.1.2 | Configure HTTPS/TLS, Secrets & Access | Configure Let's Encrypt/TLS, production environment secrets, permissions and exposed routes. | Dev 4 (Ops) | 1 | 10.1.1 | 2026-12-02 | 2026-12-02 |  |  | Not Started
10.1.3 | Configure Production Queue Worker & Scheduler | Configure supervised background worker and Laravel scheduler according to approved hosting plan. | Dev 4 (Ops) | 1 | 10.1.1, 8.1.1 | 2026-12-02 | 2026-12-02 |  |  | Not Started
10.2 | Database Readiness & Recovery | Prepare controlled migrations, seed data and database recovery steps. |  | 2 | - | 2026-12-02 | 2026-12-03 |  |  | Not Started
10.2.1 | Document Migrations, Safe Seeds & Rollback | Record migration order and rollback procedure; do not seed illustrative student credentials into production. | Dev 3 (DB) | 1 | 1.3.3, 10.1.1 | 2026-12-02 | 2026-12-02 |  |  | Not Started
10.2.2 | Verify Backup/Restore Checklist | Test the approved database backup/restore steps and record results; specific RPO/RTO remains a decision item. | Dev 4 (Ops) | 1 | 10.2.1, 0.2.3 | 2026-12-03 | 2026-12-03 |  |  | Not Started
10.3 | Deployment & Smoke Test | Publish the release candidate and verify the main role flows. |  | 6 | - | 2026-11-30 | 2026-12-05 |  |  | Not Started
10.3.1 | Build & Deploy Approved Release Candidate | Promote the approved, tested application build to the production environment. |  | 5 | - | 2026-11-30 | 2026-12-04 |  |  | Not Started
10.3.1.1 | Build Frontend Assets | Produce production React/Vite assets; the Vite dev server is not used in production. | Dev 1 (UI) | 1 | 9.3.6 | 2026-11-30 | 2026-11-30 |  |  | Not Started
10.3.1.2 | Apply Laravel Configuration & Database Migrations | Apply approved configuration and forward migrations using the release checklist. | Dev 2 (API) | 1 | 9.3.6, 10.1.2, 10.1.3, 10.2.1 | 2026-12-03 | 2026-12-03 |  |  | Not Started
10.3.1.3 | Publish Application Release | Deploy built assets and backend code to the approved server path. | Dev 4 (Ops) | 1 | 10.3.1.1, 10.3.1.2 | 2026-12-04 | 2026-12-04 |  |  | Not Started
10.3.2 | Run Production Smoke Tests | Verify login, registration, event publishing, QR/manual attendance, organizer views, admin access and CSV export. | SQA | 1 | 10.3.1.3 | 2026-12-05 | 2026-12-05 |  |  | Not Started
10.4 | Documentation & Handover | Deliver the project artifacts agreed in the development agreement. |  | 2 | - | 2026-12-05 | 2026-12-06 |  |  | Not Started
10.4.1 | Prepare Technical Setup & Deployment Documentation | Document configuration, API boundaries, dependencies, queue/scheduler and operating procedures. | Dev 2 (API) | 1 | 10.3.1.3 | 2026-12-05 | 2026-12-05 |  |  | Not Started
10.4.2 | Prepare User/Admin Guide & Source Handover | Prepare basic instructions and hand over project source/configuration and relevant deliverables. | Dev 1 (UI) | 1 | 9.3.6, 10.3.1.3 | 2026-12-05 | 2026-12-05 |  |  | Not Started
10.4.3 | Final Acceptance & Release Closeout | Submit acceptance evidence and complete final handover under the agreed review process. (Contract §§4, 10) | Client + Dev | 1 | 10.3.2, 10.4.1, 10.4.2 | 2026-12-06 | 2026-12-06 |  |  | Not Started

## Legend & Notes
WBS Legend
Level 1 - Module/Phase | Top-level project phase, e.g., Platform Foundation & Shared Architecture.
Level 2 - Task / Workstream | Core function within a phase, e.g., Login, Event Registration, Reporting.
Level 3 - Work Package | Deliverable step required to complete a task, e.g., Build Form, Implement Service.
Level 4 - Detailed Work Package | A further breakdown, e.g., generate separate QR tokens, then render/download.
Planning Notes
Source basis | Based on Attendly SRS v1.0 draft, HLD 1.0, LLD 1.0, supplied ERD, Web Architecture image, Event Attendance UI PDF and development agreement.
Planned date basis | Planned start: Monday, 12 Oct 2026. Planned deadline: Sunday, 6 Dec 2026. These dates were supplied by the project owner.
Schedule method | Duration estimates use elapsed calendar days so the 12 Oct–6 Dec plan can include parallel workstreams and weekend activity. If the team will not work weekends, re-level dates before treating this as a committed schedule.
Predecessors | Predecessor(s) lists WBS code(s) that must finish first; '-' means no predecessor.
Parent rows | Parent rows show a roll-up date range across their descendant work packages; the duration is the elapsed calendar-day span, not the sum of parallel task durations.
Actual dates | Date Started (Actual) and Date Finished (Actual) are blank for the team to fill in during execution.
Assignment | Dev 1 (UI), Dev 2 (API), Dev 3 (DB), Dev 4 (Ops), SQA, QA 1 / Client are illustrative roles; replace with actual team members.
Status | Rows default to Not Started. Use the dropdown for Not Started, In Progress, Blocked, In Testing or Completed.
Estimate limitation | AI-assisted estimate: routine UI scaffolding, CRUD/API boilerplate, test-case drafting and documentation are shortened more aggressively; approval, security review, integration, UAT and human verification retain time. Leaf task estimates reduced from 256 to 162 days in aggregate (about 37%); parallel tasks overlap, so this is not the total project length. Estimates require team review.
WBS traceability | Descriptions cite relevant FR-AUTH, FR-STU, FR-REG, FR-EVT, FR-ATT, FR-ORG, FR-ADM, FR-NOT requirements and acceptance scenarios AT-001 to AT-010 where useful.
Core ERD baseline | Five core entities: users, event_organizers, events, registrations and attendances. Supporting profile, QR, notification, moderation and audit storage requires approval where not present in the ERD.
Decision gates | Approve school-domain verification, role permissions, status enums, registration uniqueness/waitlist, QR expiry/replay, email provider, CSV columns, audit/privacy retention, auth/API boundaries, infrastructure targets, accessibility and performance.
Scope control | Features outside the agreed scope are change requests requiring approval under the software development agreement.
Security rule | Keep authorization, capacity, timestamps, registration/attendance state transitions and QR validity server-side. Do not trust browser-supplied role, timestamp or capacity values.
Deployment baseline | Linux VPS/server, Nginx, PHP-FPM, Laravel 13/PHP, MySQL 8.4 LTS, Redis, queue worker, scheduler and HTTPS/Let's Encrypt.
Testing exit | QA covers unit, frontend component/browser, API/integration, security/concurrency, AT-001 to AT-010, UAT and in-scope defect correction.
Deployment sequencing | Production setup and go-live are scheduled after UAT sign-off, following the dependency convention in the sample CRUD WBS.
Source status | The SRS, HLD and LLD are review/design drafts. Unresolved choices are treated as approval-gated decisions rather than final requirements.
Resource leveling | Dates follow logical predecessors and assume parallel workstreams, including overlap across assigned roles. Confirm actual team capacity and availability; AI speeds drafting/coding but does not replace human review or acceptance.